## Impl or Pilot (sample)
Please see Budget Instructions at end of Application form. Enter data in white cells only. Add rows and adjust totals if necessary.
Standard Budget Form (Implementation or Pilot Project)
| Grantee Organization Name: | SAMPLE
| Project Title: | SAMPLE
|  | Expense Category |  |  |  | Total | Cost Sharing
| Task | Related-Party Labor (not more than 15% of any Phase) | Contractor Expense (including any Contractor-Paid Equipment or Materials) | Equipment and Materials (if not included under Contractor Expense) | Other Direct Costs (e.g. fees, freight)* | Total | MassCEC Grant for Phase ($) | Grantee Share ($)
Design Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Initial design | 2000 | 60000 |  |  | 62000
| Subcontractor A |  |  |  |  | 0
| Subcontractor B |  |  |  |  | 0
| Application for DEP recycling permit | 2000 |  |  |  | 2000
| Application for air quality permit |  | 5000 |  |  | 5000
| Interconnection application |  | 4000 |  |  | 4000
| Design modifications, if necessary | 1000 | 6000 |  | 2000 | 9000
| Interconnection study |  | 30000 |  |  | 30000
Design Phase totals |  | 5000 | 105000 | 0 | 2000 | 112000 | 80000 | 32000
% of Phase Total** |  | 4.464% |  |  |  |  | 71.43% | 28.57%
Construction Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Equipment order (type) |  |  | 500000 | 30000 | 530000
Subcontractor C
Subcontractor D
| Equipment order (type) |  |  | 200000 |  | 200000
| Equipment order (type) |  |  | 280000 |  | 280000
| Site work, construction |  |  | 10000 |  | 10000
| Joe's Excavating (related party) | 60000 |  |  |  | 60000
| ACME Concrete |  | 50000 |  |  | 50000
| Equipment installation |  |  | 200000 |  | 200000
| Plumbing |  | 40000 | 30000 | 1000 | 71000
| Electrical |  | 50000 | 20000 | 1200 | 71200
| Complete interconnection |  |  | 100000 |  | 100000
| Construction Oversight/PM |  |  | 20000 |  | 20000
| Commissioning |  | 15000 |  |  | 15000
| Data Acquisition Sys; report to PTS |  | 8000 |  |  | 8000
| Contingency |  |  |  |  | 40000
Construction Phase totals |  | 60000 | 163000 | 1360000 | 32200 | 1655200 | 420000 | 1235200
% of Phase Total** |  | 3.625% |  |  |  |  | 25.37% | 74.63%
Budget Summary
Total Project Costs, All Phases | [5 empty] | 1767200 | Percentage of Total
Total MassCEC Grant Request** (enter requests in column H (white cell) in each Phase section above) | [5 empty] | 500000 | 28.29%
Total Grantee Cost Share | [5 empty] | 1267200 | 71.71%
* See Budget Instructions for Allowable Expenses
** Please review instructions for cost share requirements and maximum amount you may request

## Impl or Pilot (blank)
Please see Budget Instructions at end of Application form. Add rows and adjust totals if necessary.
Appendix 6 Budget Form (Implementation or Pilot Project)
Grantee Organization Name:
Project Title:
|  | Expense Category |  |  |  | Total | Cost Sharing
| Task | Related-Party Expense (not more than 15% of any Phase) | Contractor Expense (including any Contractor-Paid Equipment or Materials) | Equipment and Materials (if not included under Contractor Expense) | Other Direct Costs (e.g. fees, freight)* | Total | MassCEC Grant for Phase ($) | Grantee Share ($)
Design Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Initial design |  |  |  |  | 0
| Subcontractor A |  |  |  |  | 0
| Subcontractor B |  |  |  |  | 0
| Application for DEP recycling permit |  |  |  |  | 0
| Application for air quality permit |  |  |  |  | 0
| Interconnection application |  |  |  |  | 0
| Design modifications, if necessary |  |  |  |  | 0
| Interconnection study |  |  |  |  | 0
Design Phase totals |  | 0 | 0 | 0 | 0 | 0 |  | 0
% of Phase Total** |  | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
Construction Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Equipment order (type) |  |  |  |  | 0
| Subcontractor C |  |  |  |  | 0
| Subcontractor D |  |  |  |  | 0
| Equipment order (type) |  |  |  |  | 0
| Equipment order (type) |  |  |  |  | 0
| Site work, construction |  |  |  |  | 0
| i.e. Joe's Excavating |  |  |  |  | 0
| i.e. ACME Concrete |  |  |  |  | 0
| Equipment installation |  |  |  |  | 0
| Plumbing |  |  |  |  | 0
| Electrical |  |  |  |  | 0
| Complete interconnection |  |  |  |  | 0
| Construction Oversight/PM |  |  |  |  | 0
| Commissioning |  |  |  |  | 0
| Data Acquisition Sys; report to PTS |  |  |  |  | 0
| Contingency |  |  |  |  | 0
Construction Phase totals |  | 0 | 0 | 0 | 0 | 0 |  | 0
% of Phase Total** |  | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
Budget Summary
Total Project Costs, All Phases | [5 empty] | 0 | Percentage of Total
Total MassCEC Grant Request** (enter requests in column H (white cell) in each Phase section above) | [5 empty] | 0 | #DIV/0!
Total Grantee Cost Share | [5 empty] | 0 | #DIV/0!
* See Budget Instructions for Allowable Expenses
** Please review instructions for cost share requirements and maximum amount you may request

## Supporting Sched
Supporting Schedule
Task | Detail (e.g., Company/Vendor, Item, Labor Category) | Unit Cost | Number of Units | Other | Total | Comment